## Feuil1
|  |  | First Sprint | [14 empty] | Second Sprint | [14 empty] | Third Sprint | [14 empty] | Fourth Sprint | [14 empty] | Fifth Sprint | [14 empty] | Sixth Sprint
Mission | Deadline | Duration (d) | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Christmas 1 |  |  |  |  | Christmas 2 |  |  |  |  | Week 15 |  |  |  |  | Week 16
|  |  | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Mo | Tu
Development
Environment setup |  | 3 | bar: Week 1 Th to Week 1 Fr; Week 2 Tu
Basic Learning | bar: Week 4 Mo to Week 4 We; Week 4 Fr; Week 5 We; Week 6 Mo to Week 6 Tu
Playground development | bar: Week 4 We to Week 4 Th; Week 5 Mo to Week 6 Mo; Week 6 We to Week 6 Th
Architecture implementation | bar: Week 7 Mo to Week 7 Tu; Week 7 Fr to Week 8 We
Web Deployement | bar: Week 7 We to Week 7 Th; Week 10 Tu
Basic UI | bar: Week 8 Mo; Week 10 We
Behaviour Pipeline | bar: Week 11 Tu to Week 12 Mo; Week 12 Th
Physic implementation | bar: Week 10 Th to Week 10 Fr; Week 12 Tu to Week 12 We
Enhanced UI
Customizable PG
Enhanced Behaviour Pipeline
Documentation
Goal definition |  | 2 | bar: Week 1 Tu to Week 1 We
Template and Content |  | 2 | bar: Week 2 We; Week 2 Fr
About Thymio | bar: Week 3 Tu to Week 3 We; Week 4 Fr; Week 5 Fr; Week 6 Th to Week 7 Tu; Week 7 Th to Week 7 Fr
Requirements | bar: Week 8 Th to Week 8 Fr; Week 9 Tu; Week 9 Th; Week 11 Tu; Week 12 Fr
Architecture | bar: Week 9 We to Week 9 Th; Week 11 We; Week 11 Fr
Approach | bar: Week 11 Tu; Week 11 Fr; Week 12 Fr
Results
Conclusion
Review |  | 2 | bar: Week 16 Tu to Week 16 We
Book Submission
Doc. Submission | 2020-01-16 | bar: Week 16 Mo
Video & Poster
Poster Creation |  | 1 | bar: Christmas 2 Tu
Poster Review |  | 1 | bar: Christmas 2 Th
Video Creation |  | 1 | bar: Week 15 Mo
Video Review |  | 1 | bar: Week 15 We
Poster Submission | 2020-01-03 | bar: Christmas 2 Fr
Video Submission | 2020-01-16 | bar: Week 16 Mo
Presentations & Meetings
Meetings with M. Fuhrer | bar: Week 1 Tu; Week 2 Tu; Week 4 Tu; Week 5 Tu; Week 6 Fr; Week 10 Tu; Week 11 Tu
Meeting with Expert | bar: Week 9 Fr
Copycat Defense | bar: Week 9 Fr; Week 15 Tu to Week 16 We
Final Day | bar: Week 16 Tu
Defense