## Feuil1
|  |  | First Sprint | [14 empty] | Second Sprint | [14 empty] | Third Sprint | [14 empty] | Fourth Sprint | [14 empty] | Fifth Sprint | [14 empty] | Sixth Sprint
Mission | Deadline | Duration (d) | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Christmas 1 |  |  |  |  | Christmas 2 |  |  |  |  | Week 15 |  |  |  |  | Week 16
|  |  | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Fr | Mo | Tu | We | Th | Tu
Development
Environment setup |  | 3 | bar: Week 1 Th to Week 1 Fr; Week 2 Tu
Basic Learning |  | 7 | bar: Week 4 Mo to Week 4 We; Week 4 Fr; Week 5 We; Week 6 Mo to Week 6 Tu
Playground development |  | 10 | bar: Week 4 We to Week 4 Th; Week 5 Mo to Week 6 Mo; Week 6 We to Week 6 Th
Architecture implementation |  | 6 | bar: Week 7 Mo to Week 7 Tu; Week 7 Fr to Week 8 We
Web Deployement |  | 3 | bar: Week 7 We to Week 7 Th; Week 10 Tu
Basic UI |  | 2 | bar: Week 8 Mo; Week 10 We
Behaviour Pipeline |  | 20 | bar: Week 11 Tu to Week 12 Th; Week 13 We to Week 14 We; Christmas 1 Th; Week 15 Fr to Week 16 Mo
Physic implementation |  | 4 | bar: Week 10 Th to Week 10 Fr; Christmas 1 Mo to Christmas 1 Tu
Customizable PG |  | 3 | bar: Christmas 1 We to Christmas 1 Fr
Sensor/Actuator | bar: Christmas 1 Mo to Christmas 1 Tu; Christmas 1 Th; Week 16 Mo to Week 16 Tu
Documentation
Goal definition |  | 2 | bar: Week 1 Tu to Week 1 We
Template and Content |  | 2 | bar: Week 2 We; Week 2 Fr
About Thymio |  | 10 | bar: Week 3 Tu to Week 3 We; Week 4 Fr; Week 5 Fr; Week 6 Th to Week 7 Tu; Week 7 Th to Week 7 Fr
Requirements |  | 8 | bar: Week 8 Th to Week 8 Fr; Week 9 Tu; Week 9 Th; Week 11 Tu; Week 12 Fr to Week 13 Tu
Architecture |  | 8 | bar: Week 9 We to Week 9 Th; Week 11 We; Week 11 Fr; Week 13 Mo to Week 13 Tu; Christmas 1 Fr; Week 15 Mo
Approach |  | 12 | bar: Week 11 Tu; Week 11 Fr; Week 12 Th to Week 13 Tu; Week 14 Th to Week 14 Fr; Christmas 1 Fr; Week 15 Mo to Week 15 We
Results | bar: Week 15 We to Week 15 Fr
Conclusion | bar: Week 15 Th to Week 15 Fr
Review and corrections |  | 2 | bar: Week 16 Tu to Week 16 We
Book Creation |  | 1 | bar: Week 15 Mo
Book Review |  | 1 | bar: Week 15 Fr
Book Submissions | 2020-01-13 | x | bar: Week 15 Tu; Week 16 Mo
Doc. Submission | 2020-01-16 | x | bar: Week 16 Th
Video & Poster
Poster Creation |  | 1 | bar: Week 15 Mo
Video Creation |  | 1 | bar: Week 16 Mo
Video Review |  | 1 | bar: Week 16 Tu
Poster Submission | 2020-01-03 | x | bar: Christmas 2 Fr to Week 15 Mo
Video Submission | 2020-01-16 | x | bar: Week 16 Th
Presentations & Meetings
Meetings with M. Fuhrer | bar: Week 1 Tu; Week 2 Tu; Week 4 Tu; Week 5 Tu; Week 6 Fr; Week 10 Tu; Week 11 Tu; Week 12 Fr; Week 14 Tu; Week 15 Tu
Meeting with Expert | bar: Week 9 Fr
Presentation |  | 2 | bar: Week 16 We to Week 16 Th
Final Day | 2020-01-17 | x | bar: Week 16 Tu
Defense | 28.01.2020 16.00